## Milestones (hidden)
Milestones for CFRS plan and work - engagement strategy for focus group
Week of | Milestone from Project Plan | Topics
2021-03-04 | Finalize value proposition and guiding principles | Understand Budget Act Requirements
Align on reporting that is already done
Establish Advisory Group charge/roles
Understand timeline for the work and ultimate deliverable
Discuss value to be had from this work
Start discussion on value proposition and guiding principles
2021-03-18 | Propose Rule-Making Framework | Establish value proposition
Establish guiding principles
Discuss decision making framework and timeline for decisions
Discuss key decisions: Key terms
2021-04-01 | Propose Draft Reporting Framework | Discuss key decisions: Inclusions/Exclusions
Discuss key decisions: Budget Expenditure Categories
Share draft reporting framework for feedback
2021-04-15 | Propose Draft Rules | Discuss key decisions: Define school-level reporting rules
Discuss key decisions: Define school-level count methodology
Share revised reporting framework w/ real data
2021-04-29 | Propose Final Rules | Discuss implementation issues
| Propose Draft Rules | Revisit full suite of decisions for rules
Revisit revised reporting framework w/ real data
2021-05-13 | Draft Deliverables Review | Discuss feedback on Standards Handbook
Continue discussion on implementation issues
2021-05-27 | Final Deliverables Review | Final review of Standards Handbook
Discuss accompanying recommendations (data collection, visualization, etc.)
2021-06-10 | Close-out | Discuss next steps
Formal close out

## Project Summary (hidden)
#REF!
Project plan
#REF!
|  | Key Milestones | Proposed Dates | Complete? | Status | Notes
A |  | Fact-base Development and Data Analysis | 2/8 - 3/30 | N | 3 | Data request submitted week of 2/1
B |  | Focus Group | 3/1 - 5/24 | N | n/a
C |  | Standards Reporting Framework Development | 3/1 - 4/30 | N | n/a
D |  | Standards Rule Making | 2/15 - 5/1 | N | n/a
E |  | Standards Handbook Development | 2/22 - 5/15 | N | n/a
F |  | Final Deliverables / Approval | 4/30 - 5/31 | N | n/a
3 | = On schedule to meet milestone
2 | = Potential issues to meet milestone
1 | = Likely to miss milestone, significant issues to address
= n/a - activity not yet commenced

## Data Request (hidden)
#REF!
Initial Data Request
a) | Current financial and student count/demographic data reporting requirements (for OSSE, DME and PCSB) (ideally, a copy of DCPS + 1 Charter LEA’s full suite of reporting)
b) | FY20 sample LEA financial data for report modeling (DCPS + 2-3 Charter LEAs; chart of accounts detail for budget and actual expenditures)
c) | FY20 Student/demographic reporting data for each sample LEA.

## Foundation Categories (hidden)
Personnel (Salaries, Benefits, Bonuses, Stipends)
Classroom Staff-Teachers: Teachers
Classroom Staff-Other: Aides
Substitutes
Schoolwide Staff: Coaches, librarian, program coordinator, counselors, social workers, and psychologists, etc.
School Administration: Principal, Assistant Principal, Administrative Aide, Business Manager, Clerks, etc.
Facility Operations Support: Maintenance, custodial, security staff (if FTE)
Central Management: Non-school-level Central Administration, Instructional Support, Business, Non-Instructional Services, etc.
Non-Personnel
Instructional Support: Professional development and school improvement efforts
Direct Services to Students: Texts, Instructional Technology, Sports/Athletics, Student Services
Food Service
Nonpersonal services/programs: Field trips, school-level non-classroom supplies and materials
Other school-based costs: Technology, miscellaneous
Facility Operations Support: Non-personnel facilities costs - contracted maintenance, custodial, security; utilities (excludes rent and debt service)
Facility Occupancy: Rent Payments, Debt Service (Principal and Interest Payments)
Central Management: Non-personnel costs for Central Administration, Instructional Support, Business, and Non-Instructional Services

## LEA data request (hidden)
Public Prep Schools | #REF!
Afton Partners Financial Data Request – September 2019 | Afton Partners data request
*please note Afton would greatly appreciate receiving data in an ‘unlocked’ MS Excel format, to the extent possible | *please note Afton would greatly appreciate receiving data in an ‘unlocked’ MS Excel format, to the extent possible
Outstanding Items (TBD)
Data |  |  |  |  | Notes
|  |  | FY20A | FY21B
| a) | UPSFF Funding Allocation Calculations
i. Final UPSFF calculations for allocations to LEAs
|  | ii. All relevant data used in calculating each current component of the UPSFF |  |  | with detail on enrollment figures used for each UPSFF student need/funding weight category
| b) | Available expenditure and revenue data from DCPS and Charter schools
|  | i. Most recent fiscal year actual school-level expenditure detail and current year budget expenditure detail for each LEA, presented in most granular level of expenditure detail possible (expenditure lines include account-string detail with school and central location codes) |  |  | If possible, this data includes data points on sources of funds for each expenditure line (i.e. Title-funded expenditures vs. UPSFF-funded expenditures)
ii. Most recent fiscal year actual revenue detail and current year budget revenue detail for each LEA, focusing on identifying UPSFF funds allocated to schools. This may be used as a proxy for quantifying each school’s foundation-funded expenditures.
iii. Chart of accounts mapping for each LEA, with definitions for fund, function, object, location, etc. codes used
iv. Salary scales and associated labor contracts, if applicable
v. Non-Operating Expenditure detail for Debt Service and Capital Expenditures not included in the operating expenditure actuals and budget - FY21 budget and FY20 actual
| c) | List of all schools (per LEA) as of for FY20 and FY21 |  |  | (e.g. charter authorizations), including description of program design by school (dual-language, CTE, etc.)
| d) | School-level enrollment counts (by grade, if possible) including total at-risk student count, total ELL student count, and total SPED student count (UPSFF need weight categories); Please include the following categories of students as well: Pre-K students served, Outplaced students sent to other school networks, Outplaced students received from other school networks, Alternative Students, Adult Learners

## Afton Project Plan (hidden)
Week Beginning
Activity |  | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07
| Milestone | 2021-02-08: Project Kickoff Meeting; 2021-03-01: Kickoff Advisory Group; 2021-03-08: Draft rule-making framework; 2021-03-15: LEA data ready for modeling; propose rule-making framework; 2021-03-29: Propose reporting format to Advisory Group; 2021-04-12: Propose draft rules to Advisory Group; 2021-04-26: Propose final rules to Advisory Group; 2021-05-10: Advisory Group Draft Standards Handbook Sign-off; 2021-05-17: Draft Deliverable; 2021-06-07: Final Deliverable
Project Planning and Management
Draft project charter, project plan | bar: 2021-02-08
Kickoff Meeting with DC DME | bar: 2021-02-08
Kickoff Meetings with other key agencies (OSSE, DC PCSB) | bar: 2021-02-08 to 2021-02-15
Regular Project Updates and Meetings | bar: 2021-02-15 to 2021-06-07
Project Close-out | bar: 2021-06-07
Fact-base Development and Data Analysis
Goal: ground the work in research, facts, and requirements; have data ready for mockup
Identify and review all pertinent legislation and background materials incl UPSFF | bar: 2021-02-08 to 2021-02-22
Research common financial reporting standards from other states | bar: 2021-02-15 to 2021-03-08
Determine sample LEA set | bar: 2021-02-15 to 2021-02-22
Finalize data request | bar: 2021-02-08
- Financial reporting collected by OSSE, DME, PCSB
- Sample LEA data (DCPS, 2 charter LEAs) for report modeling
- Focus is on existing interim & annual reporting, charts of accounts used
Data received | bar: 2021-02-22 to 2021-03-08
Review and clean data, questions & follow ups | bar: 2021-03-01 to 2021-03-22
Focus Group
Goal: gain stakeholder input to rules and reporting
Draft Value Proposition and Guiding Principles | bar: 2021-02-08 to 2021-02-22
Confirm Focus Group members | bar: 2021-02-08 to 2021-02-22
Focus Group Meetings | bar: 2021-03-01; 2021-03-15; 2021-03-29; 2021-04-12; 2021-04-26; 2021-05-10; 2021-05-24
Finalize Value Proposition & Guiding Principles | bar: 2021-03-01 to 2021-03-15
Standards Reporting Framework Development
Goal: develop the formatting in which data will be received
Mock up potential reporting frameworks to meet requirements | bar: 2021-03-01 to 2021-03-08
Apply data to draft reporting as rules are developed to identify issues/complexities | bar: 2021-03-08 to 2021-03-29
Share reporting format to Focus Group | bar: 2021-03-29
Conduct impact assessment | bar: 2021-03-29 to 2021-04-05
Revise/refine reporting format | bar: 2021-04-05 to 2021-04-12
Share final reporting framework with Focus Group | bar: 2021-04-12
Incorporate reporting framework into Standards Handbook | bar: 2021-04-12 to 2021-04-19
Standards Rule Making
Goal: determine the rules by which reporting must be populated
Develop draft rule-making decision framework* | bar: 2021-02-15 to 2021-03-08
Share rule-making framework with Focus Group | bar: 2021-03-15
Refine framework based on Focus Group feedback | bar: 2021-03-15
Draft answers to rules (framework questions) | bar: 2021-03-15 to 2021-03-29
Iterative discussions with Focus Group and DME on rules | bar: 2021-03-22 to 2021-04-05
Share draft rules with Focus Group | bar: 2021-04-12
Pressure test rules for areas in need of revision/refinement | bar: 2021-04-12 to 2021-04-19
Revise/refine draft rules | bar: 2021-04-19
Propose final rules to Focus Group | bar: 2021-04-26
Standards Handbook Development
Goal: develop comprehensive deliverable that complies with the Budget Act, taking into account input from Advisory Group
Develop Standards Handbook Outline | bar: 2021-02-22 to 2021-03-08
Compile rules and guidance as decisions are made and feedback received | bar: 2021-03-15 to 2021-04-05
Incorporate reporting framework into Standards Handbook | bar: 2021-04-12 to 2021-04-19
Revise as needed | bar: 2021-04-19 to 2021-04-26
Share with Focus group | bar: 2021-05-03
Final Deliverables / Approval
Goal: package final materials
Package and proof final deliverable | bar: 2021-04-26 to 2021-05-10
Draft Deliverables Shared with DME | bar: 2021-05-17
Review, feedback, and edits (who needs to review what by when?) | bar: 2021-05-24 to 2021-05-31
Final deliverable sent | bar: 2021-06-07
*Framework to include but not limited to:
Define key terms (school, student, at-risk student, etc.)
Define need for reporting of budget or actual expenditures or both
Define what is included in reporting vs. excluded
Define budget/expenditure categories
Of all the expenses determined to be included, which ones, IF ANY, should be required to be allocated to site-level, and how?
Define student count methodology for reporting along with student demographics reporting
Implementation issues: Identify factors must be considered in developing this process
(e.g. cash vs accrual, not triggering school level audits, etc.)

## Afton Project Plan_v2 (hidden)
|  | Week Beginning |  |  | Focus LEAs |  |  |  | Focus LEAs |  |  |  | Focus LEAs
Activity |  | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07
| Milestone | 2021-02-08: Project Kickoff Meeting; 2021-03-01: Kickoff Meetings with Focus LEAs; Draft rule-making framework; 2021-03-15: LEA data ready for modeling; propose rule-making framework; 2021-03-29: Propose reporting format to Focus LEAs; 2021-04-05: Propose draft rules to Focus LEAs for feedback; 2021-04-26: Propose final rules to Focus LEAs; 2021-05-17: Draft Deliverable; 2021-06-07: Final Deliverable
Project Planning and Management
Draft project charter, project plan | bar: 2021-02-08
Kickoff Meeting with DC DME | bar: 2021-02-08
Kickoff Meetings with other key agencies (OSSE, DC PCSB) | bar: 2021-02-08 to 2021-02-15
Regular Project Updates and Meetings | bar: 2021-02-15 to 2021-06-07
Project Close-out | bar: 2021-06-07
Fact-base Development and Data Analysis
Goal: ground the work in research, facts, and requirements; have data ready for mockup
Identify and review all pertinent legislation and background materials incl UPSFF | bar: 2021-02-08 to 2021-02-22
Research common financial reporting standards from other states | bar: 2021-02-15 to 2021-03-08
Determine sample LEA set | bar: 2021-02-15 to 2021-02-22
Finalize data request | bar: 2021-02-08
- Financial reporting collected by OSSE, DME, PCSB
- Sample LEA data (DCPS, 2 charter LEAs) for report modeling
- Focus is on existing interim & annual reporting, charts of accounts used
Data received | bar: 2021-02-22 to 2021-03-08
Review and clean data, questions & follow ups | bar: 2021-03-01 to 2021-03-22
Focus Group
Goal: gain stakeholder input to rules and reporting
Draft Value Proposition and Guiding Principles | bar: 2021-02-08 to 2021-02-22
Confirm Focus Group members | bar: 2021-02-08 to 2021-02-22
Focus Group Meetings | bar: 2021-03-08; 2021-04-05; 2021-04-26; 2021-05-24
Finalize Value Proposition & Guiding Principles | bar: 2021-03-01
Standards Reporting Framework Development
Goal: develop the formatting in which data will be received
Mock up potential reporting frameworks to meet requirements | bar: 2021-03-01 to 2021-03-08
Apply data to draft reporting as rules are developed to identify issues/complexities | bar: 2021-03-08 to 2021-03-29
Share reporting format with Focus LEAs | bar: 2021-03-29
Conduct impact assessment | bar: 2021-03-29 to 2021-04-05
Revise/refine reporting format | bar: 2021-04-05 to 2021-04-12
Share final reporting framework with Focus Group | bar: 2021-04-12
Incorporate reporting framework into Standards Handbook | bar: 2021-04-12 to 2021-04-19
Standards Rule Making
Goal: determine the rules by which reporting must be populated
Develop draft rule-making decision framework* | bar: 2021-02-15 to 2021-03-01
Share rule-making framework with Focus LEAs | bar: 2021-03-08 to 2021-03-15
Refine framework based on Focus Group feedback | bar: 2021-03-08 to 2021-03-15
Draft answers to rules (framework questions) | bar: 2021-03-15 to 2021-03-29
Iterative discussions with DME on rules | bar: 2021-03-22 to 2021-04-05
Share draft rules with Focus Group | bar: 2021-04-05
Pressure test rules for areas in need of revision/refinement | bar: 2021-04-12 to 2021-04-19
Revise/refine draft rules | bar: 2021-04-19
Propose final rules to Focus Group | bar: 2021-04-26
Standards Handbook Development
Goal: develop comprehensive deliverable that complies with the Budget Act, taking into account input from Advisory Group
Develop Standards Handbook Outline | bar: 2021-02-22 to 2021-03-08
Compile rules and guidance as decisions are made and feedback received | bar: 2021-03-15 to 2021-04-05
Incorporate reporting framework into Standards Handbook | bar: 2021-04-12 to 2021-04-19
Revise as needed | bar: 2021-04-19 to 2021-04-26
Share with Focus group | bar: 2021-05-03
Final Deliverables / Approval
Goal: package final materials
Package and proof final deliverable | bar: 2021-04-26 to 2021-05-10
Draft Deliverables Shared with DME | bar: 2021-05-17
Review, feedback, and edits (who needs to review what by when?) | bar: 2021-05-24 to 2021-05-31
Final deliverable sent | bar: 2021-06-07
Big Questions to Address for Rules
Occupancy Costs Exclusions/Inclusions
Private Funds Exclusions/Inclusions
Disaster Funds Exclusions/Inclusions
At Risk Reporting approach and rules
Categories of Expenditures
Reporting Framework Alignment
Review and Approval of Standards Handbook
*Framework to include but not limited to:
Define key terms (school, student, at-risk student, etc.)
Define need for reporting of budget or actual expenditures or both
Define what is included in reporting vs. excluded
Define budget/expenditure categories
Of all the expenses determined to be included, which ones, IF ANY, should be required to be allocated to site-level, and how?
Define student count methodology for reporting along with student demographics reporting
Implementation issues: Identify factors must be considered in developing this process
(e.g. cash vs accrual, not triggering school level audits, etc.)

## At Risk supplemetal report
SAMPLE AT RISK FUNDING EXPENDITURE REPORT
School Name: |  |  | Example School 1
LEA Name: |  |  | Example LEA 1
At Risk Student Count |  |  | XXX
At Risk Student % |  |  | XX%
Instructions
This report is intended to provide insight into budgeted and actual expenditures associated with At-Risk Funding. This is a school-level report; a report must be provided for each school/school campus within an LEA. Any budgeted or actual expenditures managed at the LEA/central-level should be allocated to schools based on the students they are intended to serve. There are three parts to this report:
Part A: Please submit an overview of the programs, initiatives, and/or activities that were budgeted for or expended on with At Risk Funds in SY20XX-20YY.
Part B: Please submit a report of budget and actual spend plans using At-Risk Funds for the school year 20XX-20YY with a specific breakdown of programs, initiatives, and activities funded with At-Risk Funds
Part C: Please provide data regarding intended goals and outcomes for the use of at-risk funds. See sample report for guiding questions for this section.
Part D: Please provide a narrative on how your strategies were identified and how your At-Risk Funding aligns with other sources of funds.
Please direct questions on completion of this report to xxxx@xxxx.xxx
PART A: DESCRIPTION OF MAJOR PROGRAMS, INITIATIVES, AND ACTIVITIES
Social-Emotional Support Staff....
Additional Instruction & Support Staff....
Contracted Additional Instruction & Support....
PART B: BUDGETED AND ACTUAL EXPENDITURES | Budget | Actual | Variance
Social-Emotional Support Staff | 1120000 | 1000000 | -120000
Additional Instruction & Support Staff | 200000 | 220000 | 20000
Contracted Additional Instruction & Support | 32500 | 32500 | 0
ESTIMATED TOTAL | 1352500 | 1252500 | -100000
PART C: Intended Goals and Outcomes
Student outcomes - projected and actual outcomes. Some questions that may guide this section include - What were the indented outcomes of the initiatives included in this report? How might the school and/or LEA leadership convey the impact of these initiatives on student performance, retention, attendance, equity or any other factors to support at-risk students?
PART D: CONTEXTUAL NARRATIVE (Optional)
Development of plans:
Interaction with other funding sources:
Additional context:

## Reporting Framework_v2 (hidden)
Absolute Dollars ($1000's)
Budget Expenditures
| Site-level | [7 empty] | Central Allocations | [7 empty] | Total Site + Central | [7 empty] | Exclusions from Reporting
Schools | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Site-level Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Central Allocations Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Total Included | Capital Expenditures | Construction and Capital Improvements | Community Services | Total Exclusions | Total Expenditures
School A
School B
School C
School D
School E
LEA Total
Actual Expenditures
| Site-level | [7 empty] | Central Allocations | [7 empty] | Total Site + Central
Schools | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Site-level Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Central Allocations Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Total Included | Capital Expenditures | Construction and Capital Improvements | Community Services | Total Exclusions | Total Expenditures
School A
School B
School C
School D
School E
LEA Total
Budget H/(L) Actual
| Site-level | [7 empty] | Central Allocations | [7 empty] | Total Site + Central
Schools | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Site-level Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Central Allocations Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy | Food Services | Total Included | Capital Expenditures | Construction and Capital Improvements | Community Services | Total Exclusions | Total Expenditures
School A
School B
School C
School D
School E
LEA Total
Per Pupil | Total Student Count
School | Budget | Actual
School A
School B
School C
School D
School E
LEA Total
Budget Expenditures
| Site-level | [7 empty] | Central Allocations | [7 empty] | Total Site + Central
Schools | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Site-level Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Central Allocations Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Total Included | Capital Expenditures | Construction and Capital Improvements | Community Services | Total Exclusions | Total Expenditures
School A
School B
School C
School D
School E
LEA Total
Actual Expenditures
| Site-level | [7 empty] | Central Allocations | [7 empty] | Total Site + Central
Schools | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Site-level Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Central Allocations Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Total Included | Capital Expenditures | Construction and Capital Improvements | Community Services | Total Exclusions | Total Expenditures
School A
School B
School C
School D
School E
LEA Total
Budget H/(L) Actual
| Site-level | [7 empty] | Central Allocations | [7 empty] | Total Site + Central
Schools | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Site-level Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Central Allocations Included | Instructional staff | School administrators | Instructional supports | Educational materials | Non-educational administrative costs | Occupancy - Rent | Food Services | Total Included | Capital Expenditures | Construction and Capital Improvements | Community Services | Total Exclusions | Total Expenditures
School A
School B
School C
School D
School E
LEA Total